## Port list
# | Section | Subsection | SMAP plugin(s) | What it does | smappy status | smappy note | Suggested priority | Effort | Suggestion / how to port | Decision | Your priority | Your comments / changes | Work package (plan)
1 | 1. Localization (fitting workflow) |  | TifLoaderParallel, TifLoader, CameraConverter | read TIFF / MM stacks, ADU→photons | have | io/tiff, ndtiff, camera db + editor | – |  |  | done
2 | 1. Localization (fitting workflow) |  | fileFeeder | fit many stacks in a row | have | batch | – |  |  | done
3 | 1. Localization (fitting workflow) |  | cutoutImages, WFsplitter* / WFcombiner* | several channels on one chip | partly | 2-channel split handled by the 2C fitters | skip |  | skip (3-channel only if needed) | skip
4 | 1. Localization (fitting workflow) |  | ImageFilter, PeakFinder | DoG/Gauss filter, local max, cutoffs | have | detect.py (DoG, dynamic cutoff) | – |  | NMS and probability cutoff ⊘ – fine | done
5 | 1. Localization (fitting workflow) |  | ImageNormalize* (Anscombe), probability map |  | left out on purpose |  | – |  |  | skip
6 | 1. Localization (fitting workflow) |  | BG_wavelet, MedianBGcalculator, fitOnBackground, Roi_bg | background estimate before fitting | left out on purpose |  | P3 | M | only for strong, structured background (autofluorescent tissue). Wavelet à-trous is ~50 lines if ever needed. | later | P3 |  | J Later
7 | 1. Localization (fitting workflow) |  | RoiAdder | fit only inside / exclude drawn regions of the chip | missing |  | P2 | S | a region mask on candidates; cheap and saves bad fits on dirt/edges. | work on | P1 |  | A3 Fit region
8 | 1. Localization (fitting workflow) |  | RoiCutterWF | cut ROIs | have | roi.py | – |  |  | done
9 | 1. Localization (fitting workflow) |  | RoiCutterWF_group(Ext) | sum frames of one blink before fitting | missing |  | P3 | M | grouping after fitting covers most of the gain. | skip
10 | 1. Localization (fitting workflow) |  | MLE_GPU_Yiming | Gaussian / spline MLE (GPU) | have | C++ CPU; ◐ no GPU fitter | P3 |  | GPU fitter P3 – only if CPU speed is a real limit. | later | P3 | add GPU fitter | J Later
11 | 1. Localization (fitting workflow) |  | astigmatic Gaussian z (sx/sy → z), Sxsy2z* | 3D without a spline calibration | left out on purpose | (Gaussian free fits sx, sy) | P3 | S–M | spline covers it; useful only for users who have only an sx/sy calibration. | later | P3 |  | J Later
12 | 1. Localization (fitting workflow) |  | MLE_global_spline | multi-channel global fit | have | 2C (Gaussian and spline) | – |  |  | done
13 | 1. Localization (fitting workflow) |  | MLE_4Pi, Loader4PiMat, Channeldrift4Pi, RegisterLocs4Pi, Phase2z4Pi | 4Pi | missing |  | skip |  | skip unless 4Pi data comes back into use (L). | later | P3 |  | J Later
14 | 1. Localization (fitting workflow) |  | iterativeMDfitter | multi-emitter-aware single fitter | missing |  | P3 | M | for medium density; DECODE is the better answer. | skip
15 | 1. Localization (fitting workflow) |  | DECODE_fitting, Loader_decode, DECODE_training_estimates | deep-learning localization | missing |  | P2 | M | run DECODE in its own Python like uipsf.py (external worker + import of its output). Don't port the training glue as is. | later | P3 | think about decode + dcode-plex integration, also simplify from decode side | J Later
16 | 1. Localization (fitting workflow) |  | deepSMLM, TrainDeepSMLM, FalconHD2D | other high-density localizers | missing |  | skip |  | skip | skip
17 | 1. Localization (fitting workflow) |  | RadialSymmetry2D/3D | fast non-MLE localizer | missing |  | P3 | S | nice for beads/tracking; not for SMLM precision. | skip
18 | 1. Localization (fitting workflow) |  | usePeakfinder, pushLocs | pass positions through | n/a |  | skip |  | skip | skip
19 | 1. Localization (fitting workflow) |  | LocFilter | filter before saving | partly | display filter / Chain Layers | skip |  | skip | skip
20 | 1. Localization (fitting workflow) |  | OnlineReconstruction, PlotLocsPreview, autoLocSaver | live view, preview | have | live fit, fit preview | – |  |  | done
21 | 1. Localization (fitting workflow) |  | GrabFijiStacks, Arrayfeeder |  | missing |  | skip |  | skip | skip
22 | 1. Localization (fitting workflow) |  | sCMOS per-pixel variance/offset maps (calibrateCMOS) | per-pixel noise model | left out on purpose | (one variance per chip) | P3 | M | revisit only if a camera with bad pixels shows bias. | later | P3 | potentially | J Later
23 | 2. Calibration (PSF, camera, 3D) |  | calibrater3D_so / fit3Dcspline | cspline PSF from beads | have | Bead calibration window | – |  |  | done
24 | 2. Calibration (PSF, camera, 3D) |  | learnPSF_invmodeling | PSF by inverse modelling | have | uiPSF calibration | – |  |  | later | P3 | try to make more robust, look at Yimings implementation, own project | J Later
25 | 2. Calibration (PSF, camera, 3D) |  | CheckCalibration | fitted vs true bead z | have | calibrate/validation.py | – |  |  | done
26 | 2. Calibration (PSF, camera, 3D) |  | calibrate3Daberrations, correct3Daberrations, CorrectDepthDependentOffset | depth-dependent PSF / z-scaling correction (Li et al. 2018) | missing |  | P2 | M–L | needed for quantitative z deep in the sample. Simplify to: calibrate a z-correction map from beads in gel → apply as a table operation. | later | P3 | when needed | J Later
27 | 2. Calibration (PSF, camera, 3D) |  | GainOffsetFFT | camera gain/offset from data (Heintzmann 2016) | missing |  | P2 | S–M | feeds the camera database when the conversion factor is unknown. | later | P3 | if needed, low priority | J Later
28 | 2. Calibration (PSF, camera, 3D) |  | intensity_ratios_channels, ratio_field | channel intensity ratios / field dependence | partly | dual-colour calibration | P3 |  |  | skip
29 | 2. Calibration (PSF, camera, 3D) |  | calibrateDHPSF, fitDHPSF, getThresholdDHPSF | double-helix PSF | missing |  | skip |  | skip | later | P3 | if needed, if requested, low priority | J Later
30 | 2. Calibration (PSF, camera, 3D) |  | calibrateSALM, SALM*, zSALM, GetIntensitiesSALM | supercritical-angle z | missing |  | skip |  | skip (unless SALM is used again) | skip
31 | 2. Calibration (PSF, camera, 3D) |  | Biplane_getPSFxy, gradientEllipticity3D2z |  | missing |  | skip |  | skip | skip
32 | 3. Drift correction |  | driftcorrectionXYZ | cross-correlation drift, x/y/z | have | RCC; COMET as default | – |  |  | done
33 | 3. Drift correction |  | showdriftinfo | show saved drift | have | drift result redrawn | – |  |  | done
34 | 3. Drift correction |  | driftcorrection_beads, Analyse_Drift | fiducial-based drift | missing |  | P2 | M | segment bright persistent spots, average their tracks, smooth (reuse COMET's spline). | work on | P2 |  | D2 Fiducial drift
35 | 3. Drift correction |  | applyexistingdriftcorrection | apply drift of file A to file B (e.g. second channel) | missing |  | P1/P2 | S | drift_result already stores the curve; needed for sequential 2-colour. | work on | P2 |  | D1 Apply drift
36 | 3. Drift correction |  | applyPicassoDriftcorrection | apply Picasso drift file | missing |  | P3 | S |  | later | P3 | only when requested | D later
37 | 3. Drift correction |  | driftcorrection_dme | entropy-based drift (DME) | missing |  | skip |  | skip – COMET is the same class of method. | skip
38 | 3. Drift correction |  | driftcorrectionM | drift + magnification change | missing |  | skip |  | skip | change | P2 | in general: add time-dependent transformation (like magnification) to COMET (and maybe RCC, but more difficult there) | D3 COMET time-dep. transform
39 | 4. Channels: registration and colour assignment |  | RegisterLocs2 | transformation from localizations (beads, ratiometric) | have | Calibrate transform (split chip) | – |  | ◐ two cameras/two files not covered – see next row | later | P3 | add mulitple camera files when needed. | C later
40 | 4. Channels: registration and colour assignment |  | ApplyTransform, CombineChannels, AttachTransformation | apply a transform to the localizations of one channel/file, merge paired locs | missing | (the transform is used inside the 2C fit only) | P2 | S–M | one plugin "Apply transform" (choose file/channel, optionally average paired locs). Needed for two-camera setups and sequential imaging. | work on | P2 | also for images | C1 Transform
41 | 4. Channels: registration and colour assignment |  | RegisterImages, XYZdisplacement, Zdisplacement, correlationAnalysis, shiftCrossCorrelation | shift between two layers by cross-correlation | missing |  | P2 | S | reuse rcc.py's correlation; one plugin with x/y(/z). Same function as a site evaluator later. | later | P3 | general plugin to look at channel alignement over time as diagnostic (also at x1, y1 when dual-channel fit without linking). Seprate: calculate shift transformation based on layers (renderd images or loaded images) that can be used for anything. Correlation analysis is also important for structure analysis, this can be rather grouped with Ripley etc. | C2/C3 Register layers, alignment diagnostic
42 | 4. Channels: registration and colour assignment |  | QuantifyChannelDrift | relative drift between channels vs frame | missing |  | P3 | S |  | later | P3 | maybe if we add channel drift to dual-channel fitter | C3 Alignment diagnostic
43 | 4. Channels: registration and colour assignment |  | FrameDependentTransformation, Transform2C_interleaved |  | missing |  | skip |  | skip | skip
44 | 4. Channels: registration and colour assignment |  | Register3Dstacks | stitch z-stacks of slabs into whole-cell 3D | missing |  | P3 | M | only if whole-cell 3D by slab-stepping is done. | later | P3 |  | J Later
45 | 4. Channels: registration and colour assignment |  | Intensity2Channel | colour from intensity ratio | have | AssignColors (from global fit) | – |  |  | done
46 | 4. Channels: registration and colour assignment |  | Get2CIntImages2cam, Get2CIntImagesWF, Get2CIntLoc, roi2int_*, EvaluateIntensity_s, IntLoc2posN, Loc2pos | read intensities at transformed positions (salvaged fluorescence) | left out on purpose | replaced by the global 2C fit | skip |  | skip – keep the global-fit route. | later | P3 | the one thing we should at some point implemeent is to go from single-channel fits (e.g. using Gaussian model over entire camera) to dual color by associating localizations in both channels: transformation -> n1,n2, | C later
47 | 4. Channels: registration and colour assignment |  | Intensity2ManyChannels | >2 dyes from ratios | missing |  | P3 | S | generalise AssignColors to k clusters if ≥3-colour ratiometric is used. | change | P2 | check if our collor plugin aslo works for >2 colors (find >1 minimum where to split), integrate there. | C4 AssignColors >2
48 | 5. Files: load, save, export |  | Loader_auto, Loader_sml, Loader_csvAndMore, Loader_minflux(_json) |  | have | Auto, SMAP, csv, MINFLUX, smappy HDF5 | – |  |  | done
49 | 5. Files: load, save, export |  | Loader_tif, Loader_sml_Tiff, Rescale_tiff | associate a widefield TIFF | have | image layer (pixel size, x0, y0) | – |  |  | done
50 | 5. Files: load, save, export |  | Loader_settings, saver_settings, Loader_workflow | GUI settings | have | workspace / chains | – |  |  | done
51 | 5. Files: load, save, export |  | Loader_decode | DECODE output | missing |  | bundled | S | with DECODE (§1), or the csv loader with a preset mapping, S | work on | P1 |  | A2 Loaders
52 | 5. Files: load, save, export |  | (Picasso HDF5 *loading*) | not in SMAP | missing |  | P2 | S | symmetric with the export below; many users have Picasso data. | work on | P2 |  | A2 Loaders
53 | 5. Files: load, save, export |  | export_coordinates | CSV/TXT/XLS, chosen columns, all or filtered | missing |  | P1 | S |  | work on | P2 |  | A1 Export
54 | 5. Files: load, save, export |  | export_picasso_hdf5 | Picasso format | missing |  | P1/P2 | S |  | work on | P2 | combine with export_coordinates, one export plugin wiht many output options. SMAP can be another export. Options: what fields and what (filtered or not) to export | A1 Export
55 | 5. Files: load, save, export |  | SMLMsaver | save _sml.mat | missing |  | P2 | S–M | lets people go back to SMAP for what is not ported yet. | skip |  |  | A1 Export
56 | 5. Files: load, save, export |  | TifSaver | rendered image as TIFF | have | Export/Image | – |  |  | done
57 | 5. Files: load, save, export |  | VISPexport, sendDataToVR (Genuage) | 3D viewers | missing |  | P3 | S | CSV export with the right columns probably covers it. | skip
58 | 5. Files: load, save, export |  | PushToFiji |  | missing |  | skip |  | skip – export TIFF | skip
59 | 5. Files: load, save, export |  | seSaver, generalSeSaver | site-explorer data | have | ROI project storage | – |  |  | done
60 | 5. Files: load, save, export |  | Loader_ioPlugin |  | missing |  | skip |  | skip | skip
61 | 6. Table operations (`Process/Modify`) |  | MathParser, Mathematics | new field from an expression | have | Math Parser | – |  |  | done
62 | 6. Table operations (`Process/Modify`) |  | RemoveLocs, keepfiltered |  | have | Remove Localizations (ROI or selection, remove or hide) | – |  |  | done
63 | 6. Table operations (`Process/Modify`) |  | FilterFields, FilterFields2/3/4 | apply a filter as a step | have | Chain/Layers | – |  |  | done
64 | 6. Table operations (`Process/Modify`) |  | DefineMainCoordinates | use other fields as x/y/z | have | render axes | – |  |  | done
65 | 6. Table operations (`Process/Modify`) |  | CombineFiles | merge loaded files into one table | partly | files appended with filenumber | P3 | S | check what is missing (saving one merged file?). | later | P3 | several open files -> one file number, change frames to be continuous | J Later
66 | 6. Table operations (`Process/Modify`) |  | Connect2Unconnect, CorrectUnconnectbyConnect | grouped ↔ ungrouped coordinates | partly | grouped table + group_id on both | skip |  | skip | later | P3 | might be good to replace standard by grouped, e.g. ot save reduced file size etc. | J Later
67 | 6. Table operations (`Process/Modify`) |  | GroupAny | combine locs with the same value of any field | missing |  | P2 | S | expose group.combine with a chosen key (track id, cluster id, site id); falls out of clustering/tracking. | later | P3 | What is this used for? other plugins calling it? | J Later
68 | 6. Table operations (`Process/Modify`) |  | RenameFields, RemoveFields |  | missing |  | P3 | S | one "Edit columns" plugin. | later | P3 |  | J Later
69 | 6. Table operations (`Process/Modify`) |  | Mirror, ReverseAxis, TransformLocsManually, ChangeCamPixelsize | geometric edits | missing |  | P3 | S | one "Transform table" plugin (flip, rotate, shift, scale/pixel size). | later | P3 | combine with apply transform? add manual shift? | C1 Transform
70 | 6. Table operations (`Process/Modify`) |  | SpatialFilterLocs | local mean/median/quantile of a field around each loc | missing |  | P2 | S | a neighbourhood column for colouring (KD-tree). Pair with neighbour density (§9). | work on | P2 | this also does local density. port functionality from SMAP, maybe extend. | B1 Neighbourhood
71 | 6. Table operations (`Process/Modify`) |  | AlternatingExcitationCorrect, ImposeSymmetry, rotSymCMERec |  | missing |  | skip |  | skip | skip |  | alternating excitation might need to be addressed though… | J Later
72 | 7. Rendering and viewing |  | render modes hist / Gauss / precision Gauss / DL, colour by field, LUTs, layers, contrast, scale bar |  | have | Render tab | – |  |  | done
73 | 7. Rendering and viewing |  | VersatileRenderer | any field vs any other | have | render axes | – |  |  | done
74 | 7. Rendering and viewing |  | per-layer shiftxy (Channel tab) | shift a layer for display | missing |  | P3 | S | becomes unnecessary once "Apply transform"/"layer shift" (§4) exists. | later | P3 | we need one plugin that can shift coordinates, also where a register localizations that reslts in a shift can easily apply that shift… Alternative: option in layer that has shift… | C1 Transform
75 | 7. Rendering and viewing |  | Viewer3DV01, sideview, Phase2z4Pi | 3D view, side view | have | 3D view (slab, rotation) | – |  |  | done
76 | 7. Rendering and viewing |  | volume3D, volume3D_hist | voxel rendering, export as stack | missing |  | P3 | M | a "render z-stack" export (slices of the 2D renderer) is the useful 80%. | work on | P3 | export as 3D stack would be useful… but could also come from 3D render export | I Rendering/movies
77 | 7. Rendering and viewing |  | VoronoiRenderer | Voronoi-density image | missing |  | P3 | S | comes almost free with Voronoi clustering (§9). | work on | P3 |  | I Rendering/movies
78 | 7. Rendering and viewing |  | Show_Raw_Data, DisplayImageTags(Tiff) | raw frames, image tags | have | raw frames, Image Tags | – |  |  | done
79 | 7. Rendering and viewing |  | SetTiffLocation | re-point to moved raw data | partly |  | P3 | S |  | skip
80 | 7. Rendering and viewing |  | ImageIntensities2Locs, intensityTiff | TIFF intensity at each loc / site | missing |  | P3 | S | a column from an image layer; trivial once asked for. | skip
81 | 7. Rendering and viewing |  | Tiff_remove_BG |  | missing |  | skip |  | skip | later | P3 | at some point we could have a simple image process plugin for background subtraction, local normalization etc to nicer render the tiffs on top of SMLM data | I Rendering/movies
82 | 8. Measurement and quality control |  | Locstatistics | photons, precision, on-time | have | Localization Statistics | – |  |  | done
83 | 8. Measurement and quality control |  | FRCresolution | FRC | have | (in Localization Precision) | – |  |  | done
84 | 8. Measurement and quality control |  | lineprofile (+ROI evaluator) | line profile with models | have | Line Profile (unbinned, AIC) | P3 |  | ◐ as a site evaluator: P3 | done
85 | 8. Measurement and quality control |  | CompareToGroundTruth |  | have | Ground Truth | – |  | CompareToGroundTruthChallenge: skip | done
86 | 8. Measurement and quality control |  | Histograms | histogram + stats of any field | partly | only the four fixed ones, and ROI Histograms | P1 | S | any column, per layer, with mean/median/std. | work on | P1 |  | A4 Histogram
87 | 8. Measurement and quality control |  | StatsVsTime | photons, locs, precision, bg … vs frame or file | partly | Image Tags shows locs/frame | P1 | S | the first thing to look at when an acquisition degrades. | work on | P1 | maybe combine with image tags, possibility to draw several values in one graph… | A5 Time course
88 | 8. Measurement and quality control |  | Vibrations | spectrum of x/y/z of beads | missing |  | P3 | S |  | work on | P1 | spectrum, but also specific zoom ins and filters | A6 Vibrations
89 | 8. Measurement and quality control |  | ImageDecorrResolution | decorrelation resolution | missing |  | skip |  | skip – SMAP's own help says it is unsuitable for SMLM. | skip
90 | 8. Measurement and quality control |  | BackgroundEstimation, correlation, storerois |  | missing |  | skip |  | skip | work on | P3 | most skip, not sure what correlations does. but we should have one plugin to calculate spatial correlations (can go together with Ripley, pair correlation etc). | B3 Spatial statistics
91 | 9. Clustering and spatial statistics — nothing exists yet |  | DBSCAN_cluster | DBSCAN, cluster id per loc + cluster table | missing |  | P1 | S–M | sklearn/scipy KD-tree; write cluster_id, return a per-cluster table (n, area, radius, density). | work on | P1 | We should have one cluster plugin with several algorithms, among them DBSCAN, but also others, maybe even template based (like we use for ROI finding). Could be a larger and general one | B2 Cluster
92 | 9. Clustering and spatial statistics — nothing exists yet |  | ClusterStatistics, SpatialPointPattern (and the MINFLUX copy) | Ripley's K/L/H, pair correlation (Sengupta 2011) | missing |  | P1/P2 | M | one plugin; edge correction and a CSR envelope by simulation; in a ROI. Pair correlation needs the blinking correction to be honest – say so on the page. | work on | P1 | one plugin for spatial statistics, still decide what. also add image correlation (2D) and cross-correlations for all. | B3 Spatial statistics
93 | 9. Clustering and spatial statistics — nothing exists yet |  | ClusterVoronoi | Voronoi-cell density, clusters by threshold (SharpViSu) | missing |  | P2 | M |  | work on | P1 | cluster to cluster plugin, density to spatial filter locs (that we should rename). | B1/B2 Neighbourhood + Cluster
94 | 9. Clustering and spatial statistics — nothing exists yet |  | density_calculator | neighbours within r per loc | missing |  | P2 | S | a column; filterable, colourable. | work on | P1 | combine with spatial filter locs. we have one plugin that looks at neighborhood of every localization, counting is one of the functions | B1 Neighbourhood
95 | 9. Clustering and spatial statistics — nothing exists yet |  | ShuffelClusterIndex | random colour per cluster | missing |  | bundled | S | part of DBSCAN (write a shuffled id). | work on | P1 | the cluster plugin can have the shuffle index functionality (also for existing clustering, just an additional button) | B2 Cluster
96 | 9. Clustering and spatial statistics — nothing exists yet |  | clusterAnalysis (ROI evaluator) | DBSCAN/k-means/GMM per site | missing |  | P2 | S | P2, S once DBSCAN exists – one evaluator, DBSCAN and GMM only. | work on | P1 | statistics on all kind of clusters (also can run on rois). | B2 Cluster
97 | 9. Clustering and spatial statistics — nothing exists yet |  | dyeblinking |  | missing |  | skip |  | skip | skip
98 | 10. Counting (molecules per cluster) |  | cmakehist, cloadhist, cfithist, csegmentcluster, locsfromSE, countingStatistics(_kinetochore) | histogram of locs/blinks per cluster, fit with a model of protein number, maturation efficiency and re-activations | missing |  | P2 | M | merge into one ROI analysis: evaluator counts blinks per site (needs grouping), analysis fits the histogram. Same pattern as NPC labelling efficiency. | work on | P2 | yes, one gneral statistics ROI analysis (and clusters). larger project, think what to include here. | B4 Counting
99 | 10. Counting (molecules per cluster) |  | NPCLabelingQuantify_s, NPCLabelingEfficiency, GetExposureTime |  | have | NPC Corners, NPC Labeling Efficiency | – |  |  | done
100 | 11. Single-particle tracking — nothing exists yet |  | SimpleTracking | link locs into tracks | missing |  | P2 | S–M | reuse group.py's linking (it is the same nearest-neighbour link with larger radius/gap); write track_id. | work on | P1 | one plugin for SPT or two plugins (under the hood two, but the tracking could be run within the analysis plugin). it does the tracking (maybe find optimized algorithm), then has many analysis options to choose from and plot. | F SPT
101 | 11. Single-particle tracking — nothing exists yet |  | AnalyzeSPT, DisplaySingleTrack, Single_tracking_analysis | MSD, diffusion coefficients, jump distances, track viewer | missing |  | P2 | M | MSD and jump-distance fit per track and pooled; track overlay in the render view. | work on | P1 | combine with tracking itself.? one project anyways, think what to implement, how to extend. | F SPT
102 | 11. Single-particle tracking — nothing exists yet |  | uTrack | external uTrack | missing |  | skip |  | skip | skip
103 | 11. Single-particle tracking — nothing exists yet |  | Dual_tracking_analysis(_old), Tracks_to_movie, MINFLUX Segment_*tracks, MotorPAINT, StepsMINFLUX* | co-tracking, MINFLUX steps | missing |  | skip |  | skip (project code) – revisit if MINFLUX tracking is a focus. | work on | P2 | Implement specific MINFLUX tools that we use, especially the stepping plugin and the dual-track analysis, tracks-to movie… make this an own project and plan from scratch what we need and how we do this. | G MINFLUX
104 | 12. ROI manager | Segment | segmentNPC (+NPCsegmentCleanup) |  | have | Segment/NPC | – |  |  | change | P2 | have one powerful segmentation plugin that does the NPC stuff, but also does clustering or other segmentation tasks. | E3 Segmenter
105 | 12. ROI manager | Segment | SiteAutoDetect, generic density segmenters |  | have | Density Peaks | – |  |  | change | P2 | combine to one segment plugin | E3 Segmenter
106 | 12. ROI manager | Segment | UseSitesInROI |  | missing |  | P2 | S | keep sites inside the drawn ROI. | work on | P3 |  | E1 ROI housekeeping
107 | 12. ROI manager | Segment | RemoveLocsOutsideSites |  | missing |  | P2 | S | shrink a file to its sites. | work on | P2 |  | E1 ROI housekeeping
108 | 12. ROI manager | Segment | files2sites, makeCellGrid, cells as a level |  | missing | (no cells) | P3 | M | cells are SMAP's middle level; probably not needed if files ~ cells. | skip
109 | 12. ROI manager | Segment | segmentBeads |  | partly | bead calibration has its own | skip |  | skip | work on | P2 | as part of segment plugin, cluster segment should cover this with right settings. | E3 Segmenter
110 | 12. ROI manager | Segment | SimulateSites |  | have | Simulate structure | – |  |  | done
111 | 12. ROI manager | Segment | segmentCME*, segmentCells*, segmentSites*, fibrilFinder, CMESiteFinder_eq, Make3Dshape, proteinES_ctrl |  | missing |  | skip |  | skip (project) | work on | P3 | partially include in the segment plugin. maybe we can have presets (NPC, CME), each wtih own model and parameters. | E3 Segmenter
112 | 12. ROI manager | Evaluate | generalStatistics, clusterStatistics |  | have | Evaluate/Statistics | – |  |  | done
113 | 12. ROI manager | Evaluate | NPCLabelingQuantify_s |  | have | NPC Corners | – |  |  | done
114 | 12. ROI manager | Evaluate | NPCgeomtryQuantify (+ Analyze NPCGeometry) |  | missing |  | P2 | M | radius, ring distance, twist; NPC as a ruler (3D calibration check). | work on | P3 | is this independent from LocMoFit? | E5 Circle / NPC geometry
115 | 12. ROI manager | Evaluate | circleFitter |  | partly | circle fit inside the NPC segmenter | P2 | S | expose as an evaluator. | work on | P2 |  | E5 Circle / NPC geometry
116 | 12. ROI manager | Evaluate | CenterSites, CenterPoints |  | missing |  | P2 | S | recentre ROIs (median / circle fit / correlation). | work on | P2 | could be also part of the segment plugin as a center all (uses whatever describes center)…. | E3 Segmenter
117 | 12. ROI manager | Evaluate | LocMoFitGUI, SMLMModelFit*, modelFitter, WeiMoFit, fit_displayer* |  | missing |  | P1/P2 | L | see §13. | work on | P2 | big project, Weiqings approach or direct portation? | H LocMoFit
118 | 12. ROI manager | Evaluate | lineprofile |  | partly | Line Profile is not a site evaluator | P3 | S |  | work on | P2 | we should overcome distinction between evaluation plugin and standard analysis plugin (evaluaton just runs on the ROI of the ROI manager) | E4 Evaluator = analysis
119 | 12. ROI manager | Evaluate | shiftCrossCorrelation, correlationAnalysis |  | missing |  | bundled | S | with §4 registration, S | change | P2 | part can be in the spatial statistics plugin with 2D correlation for analyzing structures, the other part will be in the register images plugin to see shift between rendered iages or tiffs | B3 + C2
120 | 12. ROI manager | Evaluate | clusterAnalysis |  | missing |  | bundled |  | with §9 | work on | P2 | wiht cluster stuff | B2 Cluster
121 | 12. ROI manager | Evaluate | countingStatistics |  | missing |  | bundled |  | with §10 | work on | P2 | with corresponding analysis. | B4 Counting
122 | 12. ROI manager | Evaluate | LocIndices |  | n/a | (performance hack) | skip |  | skip | skip
123 | 12. ROI manager | Evaluate | beadanalysis, beadCalibrationParameters |  | partly | bead calibration window | skip |  | skip | skip
124 | 12. ROI manager | Evaluate | selectCoordinates2Color, annotatePeaks, plot3D_annotate, movieframes, assignDist, gtLLExp, intensityTiff, CME/fibril/MINFLUX evaluators |  | missing |  | skip |  | skip | later | P3 | some aspects if needed later. intensity tiff will likely be needed. | J Later
125 | 12. ROI manager | Analyze | BatchAnalyze, EvaluateSites |  | have | chains/batch, NPC chain | – |  |  | done
126 | 12. ROI manager | Analyze | ROI histograms |  | have | Analyze/Histograms | – |  |  | done
127 | 12. ROI manager | Analyze | FilterSites |  | missing |  | P1 | S | expression over evaluation results; reuse mathparse. | work on | P1 |  | E1 ROI housekeeping
128 | 12. ROI manager | Analyze | SortROIs, SortCells |  | missing |  | P2 | S |  | work on | P1 | only sort sites | E1 ROI housekeeping
129 | 12. ROI manager | Analyze | RemoveDoubleSites |  | missing |  | P2 | S |  | work on | P2 |  | E1 ROI housekeeping
130 | 12. ROI manager | Analyze | SaveSiteParameters, ExportEvaluationsTable, SaveEval |  | partly | batch writes summary.csv; no site-table export from the window | P1 | S | export the site table (CSV). | work on | P1 | user decides what to export | E1 ROI housekeeping
131 | 12. ROI manager | Analyze | Sitenumbers2loc, Eval2loc |  | missing |  | P2 | S | site id / an evaluation value as a localization column (then filter, colour, GroupAny). | work on | P2 | decide if site number this is default. evaluation value can be interesting | E1 ROI housekeeping
132 | 12. ROI manager | Analyze | roiMontage, SMLMModelFit_gallery, siteGallery_mCME |  | missing |  | P2 | S–M | one "Gallery" figure of selected sites, sorted by a value. | work on | P3 |  | E6 Site figures
133 | 12. ROI manager | Analyze | export_tiffs, export_3Dvolumes, exportrotatedsites |  | missing |  | P3 | S |  | work on | P3 | can be combined with the roiMontage, where one just decides how to export figures (montage, tiff stack, individual tiffs, …) | E6 Site figures
134 | 12. ROI manager | Analyze | AverageSites (+_NPC, _window, ByDistance, _ModleFit, _kinetochore) |  | missing |  | P2 | M | one plugin: align by centre (+ optional rotation by cross-correlation), sum into a new table; model-based alignment comes with LocMoFit. | work on | P3 | simple one, with option to use any evaluatin result or manually drawn line in ROI for orientation. -> new table. | E7 Average sites
135 | 12. ROI manager | Analyze | ImportSitePositions |  | missing |  | P3 | S |  | work on | P3 |  | E1 ROI housekeeping
136 | 12. ROI manager | Analyze | RunAnalysisScript |  | missing |  | skip |  | skip – a Python plugin file is the script | skip
137 | 12. ROI manager | Analyze | Fisheyeview, mkMovieByFilter, splitAvrageByRank, analyzeCME*, analyzeNPC*, summarize_*, yeastCME_QC, cellLevelQC, CME_DC, PlotRingCME, AnalyzeRingCME, updatePosRot_temp, clearFailAnnotatedPeaks, beforeAvg_NPC3Dfit_multiC, LocMoFit_* export/gallery |  | missing |  | skip |  | skip, or with LocMoFit | skip
138 | 13. Model fitting of sites (LocMoFit) and averaging |  | LocMoFit (LocMoFitGUI, SMLMModelFit*, modelFitter) | fit geometric/image models to each site's localizations, model selection; drives averaging | missing |  | P1/P2 | L | Port the core only: models as density functions (ring, double ring, sphere/cap, line, point, user Python function) fitted by unbinned likelihood with precision folded in (as line_profile.py does in 1D); a site evaluator; AverageSites aligned by fitted pose. Leave out GUI model builder, image models, multi-step pipelines. | work on | P2 | see above when i discussed locmofitgui… this is own project. either port or new from weiqing | H LocMoFit
139 | 14. Movies and presentation |  | MovieRunningWindow, mkMovieByFilter | sliding-window reconstruction movie (live cell) | missing |  | P3 | S–M | one "Export movie" plugin (render frame windows → mp4/TIFF stack). | work on | P3 | as suggested | I Rendering/movies
140 | 14. Movies and presentation |  | BlinkingMoviePresentation | raw frames beside a building-up SR image | missing |  | P3 | S | same plugin, a "raw + SR" layout option; uses kept raw frames. | work on | P3 | as suggested | I Rendering/movies
141 | 14. Movies and presentation |  | makeMovieTiff, Tracks_to_movie |  | missing |  | skip |  | skip | work on | P3 | part of the SPT package (or export movie to add tracks)… | F SPT
142 | 15. Infrastructure and GUI |  | ShowHistory |  | have | History | – |  |  | done
143 | 15. Infrastructure and GUI |  | BatchAnalysis, Batchprocessor |  | have | chains + smappy-batch | – |  |  | done
144 | 15. Infrastructure and GUI |  | Undo |  | have |  | – |  |  | done
145 | 15. Infrastructure and GUI |  | SearchHelp / plugin help |  | have | pages, Help window | – |  |  | done
146 | 15. Infrastructure and GUI |  | Camera settings (cameras.mat) |  | have | camera database + editor, reads SMAP's *_cameras.mat | – |  |  | done
147 | 15. Infrastructure and GUI |  | Tutorials |  | have | (SMAP has none in the GUI) | – |  |  | done
148 | Project-specific / not rated (skip unless the project returns) |  | CME2CSide*, CME2D*, CME3DDSpherefit*, CMEeqViewCellBound, segmentCME*, segmentCells*, segmentSites*, analyzeCME*, summarize_yCME, yeastCME_QC, rotSymCMERec, SMLMModelFit_dynamicRec_mCME, siteGallery_mCME, PlotRingCME, AnalyzeRingCME, AnalyzeCME2Cside | CME / yeast | missing |  | skip |  |  | skip
149 | Project-specific / not rated (skip unless the project returns) |  | fibril*, BALM_fibril_growth, boundaryFinder | Fibrils / BALM | missing |  | skip |  |  | skip
150 | Project-specific / not rated (skip unless the project returns) |  | Platelets_*, PlotPolarization, Y_fit | Platelets, polarization, misc. projects | missing |  | skip |  |  | skip
151 | Project-specific / not rated (skip unless the project returns) |  | AverageSites_kinetochore, countingStatistics_kinetochore | Kinetochore | missing |  | skip |  |  | skip
152 | Project-specific / not rated (skip unless the project returns) |  | ClusterStatistics_MINFLUX, DCoffset_Beads_ROIs, Localizationnumber, MINFLUX_timings_scouting, Tails_analyze, Cluster_MINFLUX(_Roi), StepsMINFLUX*, MotorPAINT, Segment_*tracks (loading MINFLUX is ✅; the generic parts — clustering, tracking — come with §9 and §11) | MINFLUX analysis | missing |  | skip |  |  | work on | P2 | as discussed for MINFLUX evaluators, also for MINFLUX analysis plugins we need to decide what to port, what we need now.. | G MINFLUX
153 | Project-specific / not rated (skip unless the project returns) |  | summarizeModFit*, summarize_NPCModelSelection*, summarize_MT3D, summarizeLocprecTitration, NPC3Dfitting* | Model-fit summaries | missing |  | skip |  |  | skip
154 | Project-specific / not rated (skip unless the project returns) |  | *_old, *_forVilma, SimulateSitesYL, TestTabPlugin, FilterFields2–4, sendDataToVR (×2) | Duplicates / dead | missing |  | skip |  |  | skip

## Top priorities
# | Area | What to port | Why first | Decision | Your comments
1 | Clustering & spatial statistics | DBSCAN, Ripley's K/L and pair correlation, Voronoi density, per-localization neighbour density | Nothing at all exists, and it is the most common analysis people outside the lab do. Algorithms are small (scipy/sklearn).
2 | Export for other tools | CSV/TXT export with column choice, Picasso HDF5, SMAP _sml.mat save | Users need to get data *out*; also eases the transition from SMAP. All S.
3 | Particle averaging + LocMoFit | AverageSites (simple) now; LocMoFit (model fitting of sites) as a larger project | LocMoFit is a lab method and a reason to use the ROI manager at all.
4 | ROI-manager housekeeping | filter sites by expression, sort, remove duplicates, gallery/montage, export site table, site id → localization column | Small each; together they make the ROI manager usable for real projects.
5 | Generic histograms / stats vs time | histogram of any column; photons, precision, locs/frame, … vs frame | Basic QC people expect. S each.
6 | Drift extras | fiducial (bead) drift, apply drift from another file | Fiducials are still common; "apply existing" is trivial given drift_result.
7 | Single-particle tracking | linking into tracks (reuse group.py), MSD / diffusion analysis | Whole area missing; moderate effort; skip uTrack.
8 | Depth-dependent aberration correction | calibrate3Daberrations / correct3Daberrations (Li et al. 2018) | Needed for quantitative 3D in thick samples; lab method.

## Legend
SMAP → smappy porting list
Compiled | 2026-10-11 from jries/SMAP (plugins/, fit3Dcspline, LocMoFit, GUI) and ries-lab/SMAPpy origin/main eeae43b
Fill in (yellow columns)
Decision | work on / change / later / skip / done (drop-down)
Your priority | P1 / P2 / P3 / skip (drop-down)
Your comments / changes | free text: what to change, simplify, merge
smappy status
have | already in smappy
partly | partly, or done another way
missing | not in smappy
left out on purpose | deliberately not ported (NOTES.md says why)
Suggested priority
P1 | port soon
P2 | worth porting
P3 | only if someone asks
skip | project-specific, superseded or dead
– | nothing to do (already there)
bundled | comes with another row (named in the suggestion)
Effort (incl. page and tests)
S | a day or less
M | a few days
L | a week or more